## Overview
Sport Mate — Feature & Role Specification
Project | Sport Mate — sportswear e-commerce mobile application (PRM392)
Version | 1.1
Date | 2026-10-14
Scope | 78 features (F01–F78), mapped one-to-one to use cases UC-001–UC-078
Schedule | Start 07/09/2026 · Interaction 1 due 13/10/2026 · Interaction 2 due 21/10/2026 · Interaction 3 due 27/10/2026
Team | Nguyễn Hoàng Minh · Lê Huỳnh Nhựt Khanh · Huỳnh Trần Phước Sang · Trần Thị Hồng Mai · Trương Đoàn Minh Phúc
Tech stack | Flutter (mobile) · ASP.NET Core Web API (REST/JSON, JWT) · SQL Server (EF Core)
Source documents | USE_CASES.md · BUSINESS_RULES.md · API_DESIGN.md · MOBILE_ARCHITECTURE.md · BACKEND_ARCHITECTURE.md
How to use this workbook
• Features sheet: one row per feature (F01–F78) with Interaction (L), Deadline (M), Status (N) and Assignee (O).
• Update Status as work progresses; the progress tables here and on the Delivery Plan sheet recalculate automatically.
• API paths are relative to /api/v1. "(proposed)" marks endpoints not defined in API_DESIGN.md.
• /admin/* endpoints are shared by Staff and Admin; the app shows or hides features by role and the API checks every request.
• Priority (Must / Should / Could) is a proposal; it is not defined in the source documents.
Cell to fill in
Progress by module
Module | Feature IDs | Features | Done | % done | Roles involved
Authentication | F01–F05 | 5 | 5 | 100% | Guest, Customer, Staff, Admin
User & Profile | F06–F17 | 12 | 4 | 33.33% | Customer, Staff, Admin
Product & Catalog | F18–F42 | 25 | 18 | 72% | Guest, Customer, Staff, Admin
Inventory | F43–F45 | 3 | 0 | 0% | Staff, Admin
Shopping Cart | F46–F50 | 5 | 5 | 100% | Customer
Checkout & Orders | F51–F57 | 7 | 2 | 28.57% | Customer, Staff, Admin
Payments | F58–F60 | 3 | 0 | 0% | Customer, Staff, Admin
Coupons | F61–F67 | 7 | 0 | 0% | Customer, Admin
Reviews | F68–F72 | 5 | 0 | 0% | Guest, Customer, Staff, Admin
Wishlist | F73–F75 | 3 | 3 | 100% | Customer
Reports | F76–F78 | 3 | 0 | 0% | Admin
Total | F01–F78 | 78 | 37 | 47.44% | Guest, Customer, Staff, Admin

## Delivery Plan
Delivery Plan
Project start | 2026-09-07
Interaction schedule
Interaction | Start | Deadline | Status | Features | Total | Done | Processing | Not Start
Interaction 1 | 2026-09-07 | 2026-10-13 | Done | F01–F09, F18–F30, F38–F42, F46–F52, F73–F75 | 37 | 37 | 0 | 0
Interaction 2 | 2026-10-14 | 2026-10-21 | Processing | F10–F12, F31–F33, F43–F45, F53–F67 | 24 | 0 | 24 | 0
Interaction 3 | 2026-10-22 | 2026-10-27 | Not Start | F13–F17, F34–F37, F68–F72, F76–F78 | 17 | 0 | 0 | 17
Total | 2026-09-07 | 2026-10-27 |  | F01–F78 | 78 | 37 | 24 | 17
Team assignment
Member | GitHub | Total | % done | Features | Done | Processing | Not Start
Nguyễn Hoàng Minh | Minh2005 | 17 | 52.94% | F01–F17 | 9 | 3 | 5
Lê Huỳnh Nhựt Khanh | lehuynhnhutkhanh2004 | 15 | 33.33% | F26–F37, F65–F67 | 5 | 6 | 4
Huỳnh Trần Phước Sang | sengggggg | 21 | 61.9% | F18–F25, F46–F50, F56–F60, F76–F78 | 13 | 5 | 3
Trần Thị Hồng Mai | HM126-m | 12 | 25% | F61–F64, F68–F75 | 3 | 4 | 5
Trương Đoàn Minh Phúc | nilernous | 13 | 53.85% | F38–F45, F51–F55 | 7 | 6 | 0
Total |  | 78 | 47.44% | F01–F78 | 37 | 24 | 17
All features assigned
Formulas:
Start = [Deadline, row above]+1
Deadline = [Deadline, row above]

## Features
No. | Module | Feature ID | Use Case ID | Feature Name | Description | Roles | API Endpoint | Mobile Screen | Business Rules | Priority | Interaction | Deadline | Status | Assignee
1 | Authentication | F01 | UC-001 | Register account | Guest enters name, email and password; API validates input and password policy, checks email uniqueness, hashes the password and creates a Customer account. | Guest | POST /auth/register | Register | BR-008, BR-009, BR-071, BR-072 | Must | 1 | 2026-10-13 | Done | Nguyễn Hoàng Minh
2 | Authentication | F02 | UC-002 | Sign in | Guest submits credentials; API verifies them and account status, then issues a JWT and returns safe user info and role (used by the app to show/hide features). | Guest | POST /auth/login | Login | BR-006, BR-007, BR-078 | Must | 1 | 2026-10-13 | Done | Nguyễn Hoàng Minh
3 | Authentication | F03 | UC-003 | Sign out | User signs out; app clears local auth state and API revokes the refresh token/session if supported. | Customer, Staff, Admin | POST /auth/logout | Profile | BR-077, BR-078 | Must | 1 | 2026-10-13 | Done | Nguyễn Hoàng Minh
4 | Authentication | F04 | UC-004 | Request password reset | Guest submits an email; API returns a generic response and starts a time-limited reset process for an eligible account without disclosing whether the email exists. | Guest | POST /auth/forgot-password | Forgot Password | BR-010, BR-072 | Should | 1 | 2026-10-13 | Done | Nguyễn Hoàng Minh
5 | Authentication | F05 | UC-005 | Reset password using token | Guest submits a valid reset token and new password; API validates both, updates the password hash and invalidates the token. | Guest | POST /auth/reset-password | Reset Password | BR-009, BR-010 | Should | 1 | 2026-10-13 | Done | Nguyễn Hoàng Minh
6 | User & Profile | F06 | UC-006 | Change password | User submits current and new password; API verifies the current one, validates the new one, updates the hash and applies the session-revocation policy. | Customer, Staff, Admin | PUT /users/me/password | Profile › Change Password | BR-009, BR-011, BR-078 | Must | 1 | 2026-10-13 | Done | Nguyễn Hoàng Minh
7 | User & Profile | F07 | UC-007 | View own profile | App requests the current profile; API resolves identity from JWT claims and returns the allowed fields. | Customer, Staff, Admin | GET /users/me | Profile | BR-006, BR-011, BR-078 | Must | 1 | 2026-10-13 | Done | Nguyễn Hoàng Minh
8 | User & Profile | F08 | UC-008 | Update own profile | User edits allowed profile fields; API updates only the current user's record. Role/status cannot be changed here. | Customer, Staff, Admin | PUT /users/me | Profile › Edit Profile | BR-006, BR-011, BR-071 | Must | 1 | 2026-10-13 | Done | Nguyễn Hoàng Minh
9 | User & Profile | F09 | UC-009 | Create delivery address | Customer submits address fields; API validates and creates an address owned by the current Customer. | Customer | POST /users/me/addresses | Address Management | BR-012, BR-071 | Must | 1 | 2026-10-13 | Done | Nguyễn Hoàng Minh
10 | User & Profile | F10 | UC-010 | List own delivery addresses | Customer views the address book; API returns only addresses owned by the current Customer. | Customer | GET /users/me/addresses | Address Management | BR-006, BR-012 | Must | 2 | 2026-10-21 | Processing | Nguyễn Hoàng Minh
11 | User & Profile | F11 | UC-011 | Update own delivery address | Customer edits an address; API verifies ownership and updates it. Historical order address snapshots are not changed. | Customer | PUT /users/me/addresses/{id} | Address Management | BR-012, BR-013 | Must | 2 | 2026-10-21 | Processing | Nguyễn Hoàng Minh
12 | User & Profile | F12 | UC-012 | Delete own delivery address | Customer deletes an address; API verifies ownership and deletes or deactivates it safely without affecting order snapshots. | Customer | DELETE /users/me/addresses/{id} | Address Management | BR-012, BR-013 | Must | 2 | 2026-10-21 | Processing | Nguyễn Hoàng Minh
13 | User & Profile | F13 | UC-013 | Create user account | Admin creates a user with an allowed initial role; API validates email uniqueness and role assignment. | Admin | POST /admin/users (proposed) | Admin Panel › User Management | BR-004, BR-005, BR-008, BR-009 | Should | 3 | 2026-10-27 | Not Start | Nguyễn Hoàng Minh
14 | User & Profile | F14 | UC-014 | List and view users | Admin lists/searches users and opens a user record; API returns only permitted fields. | Admin | GET /admin/users GET /admin/users/{id} | Admin Panel › User Management | BR-005, BR-006 | Must | 3 | 2026-10-27 | Not Start | Nguyễn Hoàng Minh
15 | User & Profile | F15 | UC-015 | Update user information | Admin updates permitted user information; API validates (e.g. duplicate email) and saves. | Admin | PUT /admin/users/{id} (proposed) | Admin Panel › User Management | BR-005, BR-008, BR-071 | Should | 3 | 2026-10-27 | Not Start | Nguyễn Hoàng Minh
16 | User & Profile | F16 | UC-016 | Disable user account | Admin disables an account; API updates status and revokes sessions. The last active Admin cannot be disabled; history is preserved. | Admin | PATCH /admin/users/{id}/status | Admin Panel › User Management | BR-005, BR-007 | Must | 3 | 2026-10-27 | Not Start | Nguyễn Hoàng Minh
17 | User & Profile | F17 | UC-017 | Assign or change user role | Admin assigns an allowed role (Customer/Staff/Admin); API enforces the last-admin safeguard and later authorization reflects the new role. | Admin | PATCH /admin/users/{id}/role (proposed) | Admin Panel › User Management | BR-004, BR-005, BR-006 | Must | 3 | 2026-10-27 | Not Start | Nguyễn Hoàng Minh
18 | Product & Catalog | F18 | UC-018 | Create category | Actor submits category fields; API validates and rejects duplicate key/name. | Staff, Admin | POST /admin/categories | Admin Panel › Product & Category Mgmt | BR-015, BR-071, BR-078 | Must | 1 | 2026-10-13 | Done | Huỳnh Trần Phước Sang
19 | Product & Catalog | F19 | UC-019 | List and view categories | Actor views the category list or a category detail. | Staff, Admin | GET /categories GET /categories/{id} | Admin Panel › Product & Category Mgmt | BR-015, BR-072 | Must | 1 | 2026-10-13 | Done | Huỳnh Trần Phước Sang
20 | Product & Catalog | F20 | UC-020 | Update category | Actor edits a category; API validates and rejects conflicting unique values. | Staff, Admin | PUT /admin/categories/{id} | Admin Panel › Product & Category Mgmt | BR-015, BR-071 | Must | 1 | 2026-10-13 | Done | Huỳnh Trần Phước Sang
21 | Product & Catalog | F21 | UC-021 | Delete or deactivate category | API deletes the category only if no products reference it; otherwise deactivates or rejects. | Staff, Admin | DELETE /admin/categories/{id} | Admin Panel › Product & Category Mgmt | BR-015, BR-020, BR-073 | Must | 1 | 2026-10-13 | Done | Huỳnh Trần Phước Sang
22 | Product & Catalog | F22 | UC-022 | Create brand | Actor submits brand details; API validates and rejects duplicate key/name. | Staff, Admin | POST /admin/brands (proposed) | Admin Panel › Product & Category Mgmt | BR-015, BR-071 | Should | 1 | 2026-10-13 | Done | Huỳnh Trần Phước Sang
23 | Product & Catalog | F23 | UC-023 | List and view brands | Actor views the brand list or a brand detail. | Staff, Admin | GET /admin/brands (proposed) GET /admin/brands/{id} (proposed) | Admin Panel › Product & Category Mgmt | BR-015 | Should | 1 | 2026-10-13 | Done | Huỳnh Trần Phước Sang
24 | Product & Catalog | F24 | UC-024 | Update brand | Actor edits a brand; API validates and rejects conflicting values. | Staff, Admin | PUT /admin/brands/{id} (proposed) | Admin Panel › Product & Category Mgmt | BR-015, BR-071 | Should | 1 | 2026-10-13 | Done | Huỳnh Trần Phước Sang
25 | Product & Catalog | F25 | UC-025 | Delete or deactivate brand | API deletes the brand only if no products reference it; otherwise deactivates or rejects. | Staff, Admin | DELETE /admin/brands/{id} (proposed) | Admin Panel › Product & Category Mgmt | BR-015, BR-020, BR-073 | Should | 1 | 2026-10-13 | Done | Huỳnh Trần Phước Sang
26 | Product & Catalog | F26 | UC-026 | Create product | Actor submits product details; API validates fields, price and category/brand references, then creates the product in its initial status. | Staff, Admin | POST /admin/products | Admin Panel › Product & Category Mgmt | BR-014, BR-015, BR-018, BR-071 | Must | 1 | 2026-10-13 | Done | Lê Huỳnh Nhựt Khanh
27 | Product & Catalog | F27 | UC-027 | List and view products in admin | Actor lists/searches all products including inactive ones and opens a product detail. | Staff, Admin | GET /admin/products (proposed) GET /admin/products/{id} (proposed) | Admin Panel › Product & Category Mgmt | BR-014, BR-021 | Must | 1 | 2026-10-13 | Done | Lê Huỳnh Nhựt Khanh
28 | Product & Catalog | F28 | UC-028 | Update product | Actor edits permitted fields; API validates price, status and references. Order snapshots stay unchanged. | Staff, Admin | PUT /admin/products/{id} PATCH /admin/products/{id}/status | Admin Panel › Product & Category Mgmt | BR-015, BR-018, BR-039, BR-045, BR-071 | Must | 1 | 2026-10-13 | Done | Lê Huỳnh Nhựt Khanh
29 | Product & Catalog | F29 | UC-029 | Delete or deactivate product | API deletes the product only if it has no order references; otherwise archives/deactivates so it can no longer be purchased. | Staff, Admin | DELETE /admin/products/{id} | Admin Panel › Product & Category Mgmt | BR-014, BR-020, BR-044 | Must | 1 | 2026-10-13 | Done | Lê Huỳnh Nhựt Khanh
30 | Product & Catalog | F30 | UC-030 | Create product variant | Actor adds a size/color/SKU/price variant; API validates the parent product, unique SKU and price. | Staff, Admin | POST /admin/products/{id}/variants (proposed) | Admin Panel › Product & Category Mgmt | BR-016, BR-017, BR-018, BR-022 | Must | 1 | 2026-10-13 | Done | Lê Huỳnh Nhựt Khanh
31 | Product & Catalog | F31 | UC-031 | List and view product variants | Actor lists variants of a product or opens one variant. | Staff, Admin | GET /admin/products/{id}/variants (proposed) | Admin Panel › Product & Category Mgmt | BR-016, BR-022 | Must | 2 | 2026-10-21 | Processing | Lê Huỳnh Nhựt Khanh
32 | Product & Catalog | F32 | UC-032 | Update product variant | Actor edits size, color, SKU or price; API validates SKU uniqueness and values. Stock is changed only via inventory adjustment. | Staff, Admin | PUT /admin/variants/{id} (proposed) | Admin Panel › Product & Category Mgmt | BR-016, BR-017, BR-018, BR-039, BR-045 | Must | 2 | 2026-10-21 | Processing | Lê Huỳnh Nhựt Khanh
33 | Product & Catalog | F33 | UC-033 | Delete or deactivate product variant | API deletes the variant only if safe (stock/order references); otherwise deactivates so it cannot be purchased. | Staff, Admin | DELETE /admin/variants/{id} (proposed) | Admin Panel › Product & Category Mgmt | BR-014, BR-020, BR-022 | Must | 2 | 2026-10-21 | Processing | Lê Huỳnh Nhựt Khanh
34 | Product & Catalog | F34 | UC-034 | Add product image | Actor uploads an image or supplies an approved reference; API validates file type/size and links it to the product. | Staff, Admin | POST /admin/products/{id}/images (proposed) | Admin Panel › Product & Category Mgmt | BR-019, BR-071 | Must | 3 | 2026-10-27 | Not Start | Lê Huỳnh Nhựt Khanh
35 | Product & Catalog | F35 | UC-035 | List product images | Actor views the images linked to a product with display metadata. | Staff, Admin | GET /admin/products/{id}/images (proposed) | Admin Panel › Product & Category Mgmt | BR-019 | Must | 3 | 2026-10-27 | Not Start | Lê Huỳnh Nhựt Khanh
36 | Product & Catalog | F36 | UC-036 | Update image metadata or display order | Actor changes image metadata or display order; API validates and saves. | Staff, Admin | PUT /admin/images/{id} (proposed) | Admin Panel › Product & Category Mgmt | BR-019, BR-071 | Should | 3 | 2026-10-27 | Not Start | Lê Huỳnh Nhựt Khanh
37 | Product & Catalog | F37 | UC-037 | Delete product image | Actor removes an image; API removes the association and cleans up storage according to policy. | Staff, Admin | DELETE /admin/images/{id} (proposed) | Admin Panel › Product & Category Mgmt | BR-019 | Must | 3 | 2026-10-27 | Not Start | Lê Huỳnh Nhựt Khanh
38 | Product & Catalog | F38 | UC-038 | Browse product list | Actor opens the catalog; API returns active public products with pagination. | Guest, Customer | GET /products | Home, Product List | BR-014, BR-021 | Must | 1 | 2026-10-13 | Done | Trương Đoàn Minh Phúc
39 | Product & Catalog | F39 | UC-039 | View product details | Actor opens a product; API returns description, images, variants, price and availability. | Guest, Customer | GET /products/{id} | Product Detail | BR-014, BR-016, BR-022 | Must | 1 | 2026-10-13 | Done | Trương Đoàn Minh Phúc
40 | Product & Catalog | F40 | UC-040 | Search products | Actor searches by keyword; API returns matching active products. | Guest, Customer | GET /products?keyword= | Categories & Search | BR-021, BR-071 | Must | 1 | 2026-10-13 | Done | Trương Đoàn Minh Phúc
41 | Product & Catalog | F41 | UC-041 | Filter products | Actor filters by category, brand, price range, size and/or color; API validates and combines filters. | Guest, Customer | GET /products?categoryId=&brandId=&minPrice=&maxPrice=&size=&color= | Categories & Search, Product List | BR-021, BR-071 | Must | 1 | 2026-10-13 | Done | Trương Đoàn Minh Phúc
42 | Product & Catalog | F42 | UC-042 | Sort products | Actor picks an allowed sort field and direction; API applies stable sorting with pagination. | Guest, Customer | GET /products?sortBy=&sortOrder= | Product List | BR-021 | Should | 1 | 2026-10-13 | Done | Trương Đoàn Minh Phúc
43 | Inventory | F43 | UC-043 | View inventory by variant | Actor views current available quantity for a product or variant. | Staff, Admin | GET /admin/inventory | Admin Panel › Inventory Mgmt | BR-022, BR-026, BR-078 | Must | 2 | 2026-10-21 | Processing | Trương Đoàn Minh Phúc
44 | Inventory | F44 | UC-044 | Adjust inventory quantity | Actor submits an adjustment quantity and reason; API prevents negative stock and concurrency conflicts and records the movement. | Staff, Admin | PATCH /admin/variants/{id}/stock | Admin Panel › Inventory Mgmt | BR-023, BR-025, BR-026, BR-027, BR-075, BR-076 | Must | 2 | 2026-10-21 | Processing | Trương Đoàn Minh Phúc
45 | Inventory | F45 | UC-045 | View inventory movement history | Actor filters stock movements by variant/date and views the audit history. | Staff, Admin | GET /admin/inventory/movements (proposed) | Admin Panel › Inventory Mgmt | BR-027, BR-076 | Should | 2 | 2026-10-21 | Processing | Trương Đoàn Minh Phúc
46 | Shopping Cart | F46 | UC-046 | View own cart | Customer views their cart; API returns only their items with indicative prices. | Customer | GET /cart | Cart | BR-029, BR-031 | Must | 1 | 2026-10-13 | Done | Huỳnh Trần Phước Sang
47 | Shopping Cart | F47 | UC-047 | Add item to cart | Customer adds a variant with a positive quantity; API checks the variant is purchasable and in stock. | Customer | POST /cart/items | Product Detail | BR-022, BR-024, BR-029, BR-030 | Must | 1 | 2026-10-13 | Done | Huỳnh Trần Phước Sang
48 | Shopping Cart | F48 | UC-048 | Update cart item quantity | Customer changes the quantity; API verifies ownership and availability. | Customer | PATCH /cart/items/{itemId} | Cart | BR-024, BR-029, BR-030 | Must | 1 | 2026-10-13 | Done | Huỳnh Trần Phước Sang
49 | Shopping Cart | F49 | UC-049 | Remove item from cart | Customer removes an item; API verifies ownership and removes it. | Customer | DELETE /cart/items/{itemId} | Cart | BR-029 | Must | 1 | 2026-10-13 | Done | Huỳnh Trần Phước Sang
50 | Shopping Cart | F50 | UC-050 | Clear cart | Customer removes all items from their cart (no-op if already empty). | Customer | DELETE /cart | Cart | BR-029 | Must | 1 | 2026-10-13 | Done | Huỳnh Trần Phước Sang
51 | Checkout & Orders | F51 | UC-051 | Preview checkout and calculate totals | Customer selects address, shipping method and optional coupon; API checks prices, stock and coupon, then returns subtotal, discount, shipping and estimated total. No order is created. | Customer | POST /checkout/preview | Checkout | BR-031–BR-035, BR-056, BR-058 | Must | 1 | 2026-10-13 | Done | Trương Đoàn Minh Phúc
52 | Checkout & Orders | F52 | UC-052 | Place order | API reloads prices/stock, validates address, coupon and payment method, calculates totals and, in one transaction, creates the order with snapshots, updates stock and records coupon usage. | Customer | POST /orders | Checkout › Order Confirmation | BR-024, BR-025, BR-033–BR-039, BR-045, BR-058, BR-059, BR-074, BR-075 | Must | 1 | 2026-10-13 | Done | Trương Đoàn Minh Phúc
53 | Checkout & Orders | F53 | UC-053 | View own order history | Customer views a paginated list of their own orders. | Customer | GET /orders | Order History | BR-038, BR-044 | Must | 2 | 2026-10-21 | Processing | Trương Đoàn Minh Phúc
54 | Checkout & Orders | F54 | UC-054 | View own order details | Customer opens an order; API checks ownership and returns item snapshots, totals, delivery snapshot, order and payment status. | Customer | GET /orders/{id} | Order Detail | BR-013, BR-038, BR-039, BR-046 | Must | 2 | 2026-10-21 | Processing | Trương Đoàn Minh Phúc
55 | Checkout & Orders | F55 | UC-055 | Cancel eligible own order | Customer cancels an order in a cancellable state; API records it and restores inventory exactly once. | Customer | POST /orders/{id}/cancel | Order Detail | BR-028, BR-038, BR-040–BR-045, BR-053, BR-074, BR-075 | Must | 2 | 2026-10-21 | Processing | Trương Đoàn Minh Phúc
56 | Checkout & Orders | F56 | UC-056 | Search and list all orders | Actor searches/filters all orders by ID, status, customer or date. | Staff, Admin | GET /admin/orders | Admin Panel › Order Mgmt | BR-038, BR-043, BR-072 | Must | 2 | 2026-10-21 | Processing | Huỳnh Trần Phước Sang
57 | Checkout & Orders | F57 | UC-057 | Update order status | Actor moves an order to the next status; API validates the transition and payment/inventory conditions and records actor and time. | Staff, Admin | PATCH /admin/orders/{id}/status | Admin Panel › Order Mgmt | BR-040–BR-044, BR-046, BR-076 | Must | 2 | 2026-10-21 | Processing | Huỳnh Trần Phước Sang
58 | Payments | F58 | UC-058 | View payment status for own order | Customer views payment method, amount and status of their own order. | Customer | GET /orders/{orderId}/payment | Order Detail | BR-038, BR-046, BR-052 | Must | 2 | 2026-10-21 | Processing | Huỳnh Trần Phước Sang
59 | Payments | F59 | UC-059 | Initiate supported payment | Customer chooses COD or bank transfer; API returns instructions. Payment stays pending and is never marked paid by the client. | Customer | POST /orders/{orderId}/payment | Checkout, Order Detail | BR-046–BR-049, BR-052 | Must | 2 | 2026-10-21 | Processing | Huỳnh Trần Phước Sang
60 | Payments | F60 | UC-060 | Confirm manual bank transfer | Actor verifies the transfer externally and confirms amount/reference; API records confirmer and time once. | Staff, Admin | PATCH /admin/payments/{paymentId}/confirm | Admin Panel › Order Mgmt | BR-046, BR-048, BR-050–BR-052, BR-076 | Must | 2 | 2026-10-21 | Processing | Huỳnh Trần Phước Sang
61 | Coupons | F61 | UC-061 | Create coupon | Admin defines code, discount, validity period, eligibility and usage limits; API validates and creates the coupon. | Admin | POST /admin/coupons | Admin Panel › Coupon Mgmt | BR-054–BR-057, BR-071 | Should | 2 | 2026-10-21 | Processing | Trần Thị Hồng Mai
62 | Coupons | F62 | UC-062 | List and view coupons | Admin lists/searches coupons and opens a coupon detail. | Admin | GET /admin/coupons GET /admin/coupons/{id} (proposed) | Admin Panel › Coupon Mgmt | BR-054–BR-056 | Should | 2 | 2026-10-21 | Processing | Trần Thị Hồng Mai
63 | Coupons | F63 | UC-063 | Update coupon | Admin edits coupon fields; API validates code, dates, discount and limits. Existing orders are not affected. | Admin | PUT /admin/coupons/{id} | Admin Panel › Coupon Mgmt | BR-054–BR-057, BR-060 | Should | 2 | 2026-10-21 | Processing | Trần Thị Hồng Mai
64 | Coupons | F64 | UC-064 | Delete or deactivate coupon | Admin disables the coupon, or deletes it only if it has never been used. | Admin | DELETE /admin/coupons/{id} | Admin Panel › Coupon Mgmt | BR-055, BR-059, BR-060 | Should | 2 | 2026-10-21 | Processing | Trần Thị Hồng Mai
65 | Coupons | F65 | UC-065 | Validate coupon code | Customer enters a code; API checks status, date window, minimum order, eligible products and usage limits. No usage is consumed. | Customer | POST /coupons/validate | Checkout | BR-055–BR-059 | Should | 2 | 2026-10-21 | Processing | Lê Huỳnh Nhựt Khanh
66 | Coupons | F66 | UC-066 | Apply coupon to checkout | Customer applies a valid coupon; API recalculates the discount. The coupon is revalidated when the order is placed. | Customer | POST /checkout/preview (with couponCode) | Checkout | BR-033, BR-056–BR-059 | Should | 2 | 2026-10-21 | Processing | Lê Huỳnh Nhựt Khanh
67 | Coupons | F67 | UC-067 | Remove coupon from checkout | Customer removes the coupon; API recalculates totals without it. | Customer | POST /checkout/preview (without couponCode) | Checkout | BR-033, BR-059 | Should | 2 | 2026-10-21 | Processing | Lê Huỳnh Nhựt Khanh
68 | Reviews | F68 | UC-068 | Create product review | Eligible Customer submits a rating and text; API validates purchase eligibility, rating range and duplicate policy. | Customer | POST /products/{productId}/reviews | Product Reviews | BR-061, BR-063–BR-065, BR-071 | Should | 3 | 2026-10-27 | Not Start | Trần Thị Hồng Mai
69 | Reviews | F69 | UC-069 | View reviews | Actor views product reviews; public users see only visible reviews, Staff/Admin can see all for moderation. | Guest, Customer, Staff, Admin | GET /products/{id}/reviews | Product Detail, Product Reviews, Admin Panel › Review Moderation | BR-065, BR-072 | Should | 3 | 2026-10-27 | Not Start | Trần Thị Hồng Mai
70 | Reviews | F70 | UC-070 | Update own review | Customer edits the rating/text of their own review; moderation state follows policy. | Customer | PUT /reviews/{id} | Product Reviews | BR-062–BR-065 | Should | 3 | 2026-10-27 | Not Start | Trần Thị Hồng Mai
71 | Reviews | F71 | UC-071 | Delete own review | Customer deletes (or soft-deletes) their own review. | Customer | DELETE /reviews/{id} | Product Reviews | BR-062, BR-065 | Should | 3 | 2026-10-27 | Not Start | Trần Thị Hồng Mai
72 | Reviews | F72 | UC-072 | Moderate review | Actor approves, hides or rejects a review; API records the decision and public visibility follows it. | Staff, Admin | PATCH /admin/reviews/{id}/status | Admin Panel › Review Moderation | BR-005, BR-065, BR-076 | Should | 3 | 2026-10-27 | Not Start | Trần Thị Hồng Mai
73 | Wishlist | F73 | UC-073 | View own wishlist | Customer views their own wishlist entries. | Customer | GET /users/me/wishlist | Wishlist | BR-066 | Could | 1 | 2026-10-13 | Done | Trần Thị Hồng Mai
74 | Wishlist | F74 | UC-074 | Add product to wishlist | Customer adds a product; API prevents duplicate entries. | Customer | POST /users/me/wishlist/items | Product Detail, Wishlist | BR-066, BR-071 | Could | 1 | 2026-10-13 | Done | Trần Thị Hồng Mai
75 | Wishlist | F75 | UC-075 | Remove product from wishlist | Customer removes a product from their wishlist. | Customer | DELETE /users/me/wishlist/items/{productId} | Wishlist | BR-066 | Could | 1 | 2026-10-13 | Done | Trần Thị Hồng Mai
76 | Reports | F76 | UC-076 | View sales and order dashboard | Admin views order and revenue metrics for a valid period. | Admin | GET /admin/dashboard/summary | Admin Panel › Dashboard | BR-067–BR-069 | Should | 3 | 2026-10-27 | Not Start | Huỳnh Trần Phước Sang
77 | Reports | F77 | UC-077 | View order report | Admin views order counts and summaries by date range/status. | Admin | GET /admin/reports/orders (proposed) | Admin Panel › Dashboard | BR-067–BR-069 | Should | 3 | 2026-10-27 | Not Start | Huỳnh Trần Phước Sang
78 | Reports | F78 | UC-078 | View best-selling products report | Admin views products ranked by the agreed quantity/revenue definition for a period. | Admin | GET /admin/reports/top-products | Admin Panel › Dashboard | BR-067, BR-069, BR-070 | Should | 3 | 2026-10-27 | Not Start | Huỳnh Trần Phước Sang
Note on N1: Done / Processing / Not Start. Update as work progresses.
Note on O1: Team member who owns this feature (list from the Delivery Plan sheet).

## Roles
Role | Type | Description | Mobile area
Guest | Unauthenticated actor (not stored) | Visitor who may register, sign in, reset a password and browse, search, filter and sort the public catalog and reviews. | Auth screens, Home, Product List / Detail, Search
Customer | Authenticated role | Registered shopper who manages their own profile, addresses, cart, orders, payments, wishlist and eligible reviews. | Customer app (bottom navigation)
Staff | Authenticated role | Operational user who maintains catalog and inventory, processes orders, confirms manual bank transfers and moderates reviews. Cannot manage roles, users, coupons or reports. | Admin Panel (operational items only) + Profile
Admin | Authenticated role | Administrator with all Staff capabilities plus user and role management, coupon management and reports. | Admin Panel (all items) + Profile

## Authorization
Capability | Guest | Customer | Staff | Admin
Browse public catalog and reviews | Yes | Yes | Yes | Yes
Manage own profile and password | No | Yes | Yes | Yes
Manage own addresses, cart, orders, payments | No | Yes | No by default | No by default
Manage own wishlist and reviews | No | Yes | No | No
Manage catalog (categories, brands, products, variants, images) | No | No | Yes | Yes
Manage inventory | No | No | Yes | Yes
Process all orders | No | No | Yes | Yes
Confirm manual bank transfer | No | No | Yes | Yes
Moderate reviews | No | No | Yes | Yes
Manage coupons | No | No | No | Yes
Manage users and roles | No | No | No | Yes
View dashboard and reports | No | No | No | Yes

## Screen Visibility
Screen / Navigation item | Features | Guest | Customer | Staff | Admin
Login, Register, Forgot / Reset Password | F01, F02, F04, F05 | ● | – | – | –
Home, Product List, Categories & Search | F38, F40–F42 | ● | ● | ● | ●
Product Detail | F39, F69 | ● | ● | ● | ●
Product Detail › Add to Cart / Add to Wishlist | F47, F74 | Prompt | ● | – | –
Product Reviews › Write / Edit / Delete review | F68, F70, F71 | Prompt | ● | – | –
Cart | F46, F48–F50 | – | ● | – | –
Checkout (address, coupon, payment) | F51, F52, F59, F65–F67 | – | ● | – | –
Order History, Order Detail | F53–F55, F58 | – | ● | – | –
Wishlist | F73–F75 | – | ● | – | –
Profile, Change Password, Sign Out | F03, F06–F08 | – | ● | ● | ●
Address Management | F09–F12 | – | ● | – | –
Admin Panel › Product & Category Mgmt | F18–F37 | – | – | ● | ●
Admin Panel › Inventory Mgmt | F43–F45 | – | – | ● | ●
Admin Panel › Order Mgmt (incl. payment confirmation) | F56, F57, F60 | – | – | ● | ●
Admin Panel › Review Moderation | F69, F72 | – | – | ● | ●
Admin Panel › Coupon Mgmt | F61–F64 | – | – | – | ●
Admin Panel › User Management | F13–F17 | – | – | – | ●
Admin Panel › Dashboard & Reports | F76–F78 | – | – | – | ●
● shown · – hidden · Prompt: visible but asks a Guest to sign in

## Business Rules
ID | Rule | Group
BR-001 | Supported roles | Roles and Access Control
BR-002 | Public access | Roles and Access Control
BR-003 | Customer ownership | Roles and Access Control
BR-004 | Staff permissions | Roles and Access Control
BR-005 | Admin permissions | Roles and Access Control
BR-006 | Identity source | Roles and Access Control
BR-007 | Account status | Roles and Access Control
BR-008 | Unique email | Authentication and User Data
BR-009 | Password storage | Authentication and User Data
BR-010 | Password reset | Authentication and User Data
BR-011 | Profile update | Authentication and User Data
BR-012 | Address ownership | Authentication and User Data
BR-013 | Order address snapshot | Authentication and User Data
BR-014 | Product status | Product Catalog
BR-015 | Category and brand references | Product Catalog
BR-016 | Product variants | Product Catalog
BR-017 | Unique SKU | Product Catalog
BR-018 | Price validity | Product Catalog
BR-019 | Product images | Product Catalog
BR-020 | Referenced product deletion | Product Catalog
BR-021 | Public catalog filters | Product Catalog
BR-022 | Variant-level stock | Inventory
BR-023 | Non-negative stock | Inventory
BR-024 | Server-side stock validation | Inventory
BR-025 | Atomic inventory changes | Inventory
BR-026 | Inventory adjustment permission | Inventory
BR-027 | Inventory movement history | Inventory
BR-028 | Cancellation stock policy | Inventory
BR-029 | Cart ownership | Cart and Checkout
BR-030 | Valid cart item | Cart and Checkout
BR-031 | Cart is not a price guarantee | Cart and Checkout
BR-032 | Checkout address | Cart and Checkout
BR-033 | Server-calculated totals | Cart and Checkout
BR-034 | Monetary precision | Cart and Checkout
BR-035 | Checkout consistency | Cart and Checkout
BR-036 | Duplicate submission | Cart and Checkout
BR-037 | Cart cleanup | Cart and Checkout
BR-038 | Order ownership | Orders
BR-039 | Order item snapshot | Orders
BR-040 | Order states | Orders
BR-041 | Valid state transitions | Orders
BR-042 | Customer cancellation | Orders
BR-043 | Staff order processing | Orders
BR-044 | Historical integrity | Orders
BR-045 | Order totals are immutable snapshots | Orders
BR-046 | Separate payment and order states | Payment
BR-047 | Initial payment methods | Payment
BR-048 | Customer cannot self-confirm payment | Payment
BR-049 | COD status | Payment
BR-050 | Manual bank transfer | Payment
BR-051 | Duplicate payment confirmation | Payment
BR-052 | Payment amount | Payment
BR-053 | Refund policy | Payment
BR-054 | Unique coupon code | Promotions and Coupons
BR-055 | Coupon validity window | Promotions and Coupons
BR-056 | Coupon eligibility | Promotions and Coupons
BR-057 | Discount bounds | Promotions and Coupons
BR-058 | Coupon revalidation | Promotions and Coupons
BR-059 | Coupon usage consistency | Promotions and Coupons
BR-060 | Coupon updates | Promotions and Coupons
BR-061 | Review eligibility | Reviews and Wishlist
BR-062 | Review ownership | Reviews and Wishlist
BR-063 | Review uniqueness | Reviews and Wishlist
BR-064 | Review rating | Reviews and Wishlist
BR-065 | Review moderation | Reviews and Wishlist
BR-066 | Wishlist ownership | Reviews and Wishlist
BR-067 | Admin-only reports | Reporting
BR-068 | Revenue definition | Reporting
BR-069 | Date range validation | Reporting
BR-070 | Best-selling calculation | Reporting
BR-071 | Server-side validation | API and Data Integrity
BR-072 | Consistent errors | API and Data Integrity
BR-073 | Database constraints | API and Data Integrity
BR-074 | Transaction boundaries | API and Data Integrity
BR-075 | Concurrency | API and Data Integrity
BR-076 | Audit-sensitive actions | API and Data Integrity
BR-077 | Secret handling | API and Data Integrity
BR-078 | Authentication enforcement | API and Data Integrity